## Data
Task | Start Date | End Date | Duration | Status | Owner
1. Project Kickoff & Setup | 8/7/2025 | 8/10/2025 | 4 | Done | PM
– Create GitHub repo | 8/7/2025 | 8/8/2025 | 2 | Done | All
– Set folder structure | 8/8/2025 | 8/9/2025 | 2 | Done | Documenter
– Hold meeting #1 | 8/10/2025 | 8/10/2025 | 1 | Done | PM
2. Logical Design | 8/11/2025 | 8/14/2025 | 4 | Not Started | Analyst
– Use-Case Diagram | 8/11/2025 | 8/12/2025 | 2 | Not Started | System Analyst
– ERD Design | 8/12/2025 | 8/14/2025 | 3 | Not Started | DB Designer
3. Physical Design | 8/15/2025 | 8/18/2025 | 4 | Not Started | Lead Dev
– SQL DB Setup | 8/15/2025 | 8/16/2025 | 2 | Not Started | DB Designer
– Login Form | 8/15/2025 | 8/17/2025 | 3 | Not Started | Lead Developer
4. Core Modules | 8/19/2025 | 8/28/2025 | 10 | Not Started | Team
– Policyholders | 8/19/2025 | 8/21/2025 | 3 | Not Started | UI/UX + Dev
– Policies | 8/21/2025 | 8/23/2025 | 3 | Not Started | Dev
– Claims | 8/23/2025 | 8/25/2025 | 3 | Not Started | Dev
– Payments | 8/25/2025 | 8/27/2025 | 3 | Not Started | Dev
– Reports | 8/27/2025 | 8/28/2025 | 2 | Not Started | Analyst
5. Testing | 8/29/2025 | 8/31/2025 | 3 | Not Started | Tester
6. Final Documentation | 9/1/2025 | 9/6/2025 | 6 | Not Started | Documenter
7. Submission | 9/7/2025 | 9/7/2025 | 1 | Not Started | All